## Sheet1
Sr.No | Emp.Id | Name | Domain | Module | 2022-02-23 | 2022-02-24 | 2022-02-25 | 2022-03-01 | 2022-03-02 | 2022-03-03 | 2022-03-04 | 2022-03-07
1 | 2478456 | Shrinath Shivaji Magdum | Front-End | Forgot Passward, Manage product,processing orderes | Divison and Discussion of Flow | Forgot Passward | Forgot Passward | Manage product | Integration | Review meeeting and image/Styling | processing orderes | Documentation/PPT/Solving Error
2 | 2478988 | Kamsala Sai | Front-End | Place Order, Product,View Restaurants | Divison and Discussion of Flow | Product List | Product List | Place Order | Integration | Review meeeting and image/Styling | View Restaurants | Issue resolving
3 | 2477759 | Pandey Aishwariya Jyothi | Front-End | Login , Completed Orderes, Processing Orderes | Divison and Discussion of Flow | Login | Login | Completed Orderes | Integration | Review meeeting and image/Styling | processing orderes | Issue resolving/PPT
4 | 2479448 | Pragya Upadhyay | Front-End | Signup, Order Details, View Restaurants | Divison and Discussion of Flow | Signup | Signup | Order Details | Integration | Review meeeting and image/Styling | View Restaurants | Issue resolving
5 | 2478529 | Reddem Himabindu | Front-End | Manage - Restaurant, New Order, View Restaurants | Divison and Discussion of Flow | Manage - Restaurant | Manage - Restaurant | New Order | Integration | Review meeeting and image/Styling | View Restaurants | Issue resolving
6 | 2478066 | Alugubelly Madhuri | Back-End | User Data details | Divison and Discussion of Flow | User data | User data | Postman Tool | Integration | Table Creation | Testing the code | Junit Testing
7 | 2477622 | Koppolu Venkata Teja | Back-End | App User details, User Parchase details | Divison and Discussion of Flow | App User | User Parchase | Postman Tool | Integration | Report / Table Creation | Report | Junit Testing/PPT
8 | 24478841 | Pidugu Pravalika | Back-End | Products details | Divison and Discussion of Flow | Product | Product | Postman Tool | Integration | Table Creation | Testing the code | Junit Testing
9 | 2479031 | S Bindhu | Back-End | Restaurants details | Divison and Discussion of Flow | Restaurants | Restaurant | Postman Tool | Integration | Table Creation | Testing the code | Junit Testing
10 | 2478517 | Devarinti Anusha | Back-End | category for food details | Divison and Discussion of Flow | Category | Category | Postman Tool | Integration | Table Creation | Testing the code | Junit Testing